## Slide 1: AGILE ESTIMATION

## Slide 2: Estimating the Size - Story Points
Estimate is defined as ‘the quantified evaluation of the effort necessary to carry out a given development task.’ Estimation is done in terms of size or duration.
  Estimating the size helps in the estimation of duration, which is shown in the figure given below.
  Story points are a unit of measure for expressing the overall size of a user story, feature, or any other piece of work. A point value is assigned to each item while estimating with story points.
  Story points are relative and not absolute. A story point with a value two should be twice as much the story with the value one.
  The number of story points associated with a story represents the overall size of the story.
Desired Features
Estimate size
Estimate duration
Schedule
Notes: Notes to the Facilitator:
Explain the participants about estimating with story points.
Notes to the Participants:
Mike Cohn defines story points are a unit of measure for expressing the overall size of a user story, feature, or other piece of work. Point values are assigned to each item when estimation is done with story points. Story point values are relative ones. A story that is assigned a value two will be as twice as a story with value one. The number of story points associated with a story represents the overall size of the story. There is no strict formula for defining the story size. Story size is normally defined on the basis of the amount of effort involved in developing the feature, the complexity of developing it, the risk inherent in it, and so on.
Typically, there are two ways to get started with story points.
Select a story that is expected to be smaller, which is estimated at a value of 1 story point.
Select a medium-sized story and assign it a number somewhere in the middle of the range that is expected to be used.
Once the first story is estimated the remaining stories can be estimated by comparing them with the first story or the ones that have been estimated already. The first story will serve as the base or reference story for the second story. This way relative sizing is done using story points.

## Slide 3: 1.29 Velocity
  Velocity is defined as a measure of a team’s rate of progress, which is important to understand the story points.
  Velocity is by adding the number of story points assigned to each user story that the team completed during the iteration.
  For example, if a team completes three stories that are valued at three story points each, the velocity of the team would be nine.
  Based on the velocity of the team during the previous iteration, the estimate for the next iteration can be estimated.
  If the story point estimates of all the features are summed up, the total size estimate for the project can be done.
Following are the key details of velocity:
Notes: Notes to the Facilitator:
Explain the participants about velocity and how it helps understand the estimating story points for a project.
Notes to the Participants:
Velocity is defined as the rate of the team’s progress. Velocity is calculated by adding up the story points assigned to each user story that the team completed during the iteration. For example, if a team completes three stories that are valued at three story points each, the velocity of the team would be nine.
We’ll see how we can use velocity to estimate the size. If a team completed ten story points of work last iteration, we can assume that they will complete ten story points this iteration. Since story points are estimates of the relative size, this calculation will hold true if the team completes two five-point user stories or five two-point user stories.
The total size of any project is estimated by adding up the story points of all the desired features that make up a project. If the team’s velocity is known, we can derive the number of iterations by dividing the size by velocity. This duration can then be converted into a schedule by mapping it onto a calendar. An example of this has been given by Mike Cohn.
“For example, suppose all of the user stories are estimated and the sum of those estimates is 100 story points. Based on past experience, we know the team’s velocity to be 11 story points per two-week iteration. Since we can estimate that the project needs 9.1 iterations. We can either round that up to 10 iterations or find one point to remove so that it becomes 9 iterations. Let’s assume we go with a conservative approach and call it 10 iterations. Since each iteration is two weeks, our estimate of duration is twenty weeks. We can count forward twenty weeks on the calendar and that becomes our schedule.”

## Slide 4: 1.30 Estimating in Ideal Days
In Agile development, user stories or other tasks are estimated in ideal days.
  The story being estimated is the only thing that the developer works on
  Everything the developer needs will be on hand when they start
  There will be no interruptions
  While estimating the ideal days required to develop, test and accept a user story, it is not necessary to take into account, the overhead of the environment in which the team works.
  If this organizational overhead is ignored, ideal days can be thought of as an estimate similar to story points.
The assumptions behind ideal days estimation are as follows:
Notes: Notes to the Facilitator:
Explain how the estimate is done as ideal days.
Notes to the Participants:
On a software project, user stories or other tasks are estimated in ideal days, based on the following assumptions:
The story being estimated is the only thing that the developer works on
Everything the developer needs will be on hand when they start
There will be no interruptions
Estimating in elapsed days instead of ideal days, requires us to consider all of the interruptions that might occur while working on the particular story. If the estimate is done in ideal days, only the amount of time the story will take is only considered. In this way, ideal days are an estimate of size, although less strictly so than story points.
When organizational overhead is ignored, ideal days can be thought of as another estimate of size, similar to story points. Then, an estimate of size expressed as a number of ideal days can be converted into an estimate of duration using the velocity in exactly the same way as with story points.
When estimating in ideal days it is best to associate a single estimate with each user story. If a user story will take four programmer days, two tester days, and three product owner days, it is better to sum those and tell the story as a whole will take nine ideal days.

## Slide 5: What did You Grasp?
What is the velocity of the team that completes five user stories that have 4 story points each?
  10
  15
  20
  30
State True or False. While estimating in ideal days, it is assumed that the developer works only on the story being estimated.
  True
  False
Notes: Notes to the Facilitator:
Tell the participants that they will be going through a knowledge check question.
Answers:
1. c. 20
2. a. True

## Slide 6: 1.31 Estimating Techniques
The three most common techniques for estimating are represented in the figure below:
Agile Estimating Techniques
Expert Opinion
Analogy
Disaggregation
Notes: Notes to the Facilitator:
Explain the participants about the three techniques for estimating.
Notes to the Participants:
Three techniques are commonly used for estimating.
Expert Opinion: In this approach, expert opinion on how long some task will take or how big something will be, is sought out. The expert will provide an estimate based on gut feel or intuition or past experience. This approach is found to be less useful in Agile projects, since Agile estimating is done based on user stories or other important functionalities. Developing a functionality requires varied skill sets and Agile teams are generally cross-functional. It is difficult to find experts who can assess the effort across multiple disciplines. This approach might be suitable for a traditional project, because each task is performed by one person in traditional projects. One benefit of getting expert opinion is that it is a less time consuming option.
Analogy: In this approach, the story being estimated is compared with one or more stories. Then a relative sizing is applied and estimate is provided. A story twice as big as another story will be given an estimate twice as large. In this approach, there is no single base or universal reference. Stories for which estimates are already available are used as benchmarks estimating other stories. This process is also referred to as triangulation.
Disaggregation: Disaggregation refers to splitting down a user story into smaller, easy to estimate pieces. Projects with multiple smaller stories are easier to estimate than the ones with the single large story. Disaggregation will lead to problems if we go beyond a limit. If we disaggregate too far, the chances of forgetting tasks also increase.
In the upcoming slides, we’ll look at two commonly used Agile estimating techniques.

## Slide 7: 1.32 Planning Poker
Following are the key details of the Planning Poker game:
  Planning poker is one of the most popular gross level estimating technique, which uses Fibonacci sequence (adding previous two numbers to get the next number in the sequence) to assign point value to a story or a feature.
  Fibonacci sequence has been modified to get the following sequence for Agile estimation purposes: 0, 1, 2, 3, 5, 8, 13, 20, 40, 100.
  The numbers in the given sequence are represented in a set of playing cards as shown in the picture.
  Team members play the Planning Poker game and assign a point value to each item. The process is explained below in the notes.
  Fibonacci sequence is used as these numbers to represent relative size and this method also provide the correct level of detail for smaller and better understood projects.
40
100
20
13
8
5
3
2
1
Notes: Notes to the Facilitator:
Explain the participants about the Planning Poker game, which is used for estimating Agile.
Notes to the Participants:
Planning Poker is a game-based Agile estimating technique, based on the Fibonacci sequence. In the Fibonacci sequence, the previous two numbers are added to get the next number in the sequence (0, 1, 1, 2, 3, 5, 8, …..). For Agile estimating the sequence has been modified to get the following sequence: 0, 1, 2, 3, 5, 8, 13, 20, 40, 100. These numbers are printed on playing cards. Team members play the Planning Poker game to assign point value to each story or item. The steps in the game are as follows:
Each member in the team gets a deck of cards that read the sequence 0, 1, 2, 3, 5, 8, 13, 20, 40, 100. The team includes programmers, testers, database engineers, analysts, user interaction designers and so forth. Ideal team size is 10; the number of team members increases, it is better to split into two teams. Each team will estimate independently. Product Owner participates, but doesn’t estimate.
The moderator reads out the story or the item to be estimated. Usually, the product owner or the analyst will serve the role of the moderator. Product owner answers the questions of the estimators.
Each member of the team privately selects a card that represents his/her estimate.
When all the team members are ready with their estimates, all the cards are revealed at the same time.
If all the team members selected the card with the same number, then that number will be assigned as the point value of the item. If the cards are not the same team then they discusses the item with the emphasis placed on values.
The member who selected the lowest and the member who selected the highest value should explain the logic behind the selection.
Selection happens until the numbers converge.
For longer conversations, teams may use a 2-minute timer to timebox the session.
The process is repeated for each story or each item.
Fibonacci numbers are used, as they represent relative size and the estimate can be done quickly. This sequence also provides right estimates for smaller and better understood items. Teams have only less number of choices for assigning the point values and the estimate are done at a fast pace.
Items with a point value of 20 or higher may be considered as less-understood items. Items with point estimates between 1-13 can generally be completed in a single iteration of 1 - 4 weeks. One important thing to note here is that the points may have different meanings for different teams and team velocity is not the right way to compare productivity across the teams.

## Slide 8: 1.33 Affinity Grouping
Following are the key details of affinity grouping:
  Affinity grouping is a faster way to Agile estimating, especially when the number of items to estimate is very large.
  Stories or items that are like-sized are grouped together that results in affinity groups as shown in the picture.
  The first item is read out by the presenter to the team members and placed on the wall. The second item is then read out and compared with the size of the first item. If it is of smaller size, it goes to the left of the first one and if larger, goes to the right.
  All the items are thus read out, assessed and placed on the wall. The team then reviews the grouping and any inappropriate placement is modified.
  Once the affinity grouping is complete, point values are then assigned.
Smaller
Large
Notes: Notes to the Facilitator:
Explain the participants about affinity grouping.
Notes to the Participants:
Affinity grouping is a faster way to estimate, especially if the number of items to be estimated is large. Team members analyse and group the items or stories and group similar-sized items to get a structure like the one shown in the picture. This method is simple and fast. The method is explained as follows:
The first item is read out by the presenter to the team members and placed on the wall.
The second item is then read out and the team discusses and finds out if it is larger or smaller than the first one. It is then placed on the wall based on the team’s response. If larger it goes to the right of the first one, if smaller it will go to the left.
The third item is then read out and compared with the first two. Based on the size it is placed on the wall.
The team then gets the control to finish the remainder of the items.
The team can continue the same way of discussing and placing the items on the wall. Another faster alternative is to have each team member, select one item and place it on the wall as per their discretion. This is done with all the team members, until all the items in the project are assessed and placed on the wall.
This way, several items can be estimated in a short period. Once all the items are placed on the wall, teams then review the grouping. If any team member believes that any item is placed in the wrong group, it can be moved to the appropriate group after discussion.
Once this grouping is complete, point values are assigned to the items, based on the sequence discussed in the previous section.
Thus, this section explains the estimation procedure and techniques involved. We’ll now look into implementation of Agile in industry projects.

## Slide 9: 1.34 T-Shirt Sizes
The salient features of T-shirt sizes are as follows:
  T-Shirt sizes is a way of estimating relative sizes of features. Five different sizes Extra Small (XS), Small (S), Medium (M), Large (L), Extra Large (XL) are used for estimating the size of features.
  Using T-shirt sizes is an informal and fast way of assessing the size of backlog items.
  The picture shows how affinity grouping is done using T-shirt sizes.
  After mutual discussion and agreement of the team, a relative size is first decided, which will be medium (M) most often.
  Numbers are then assigned to the items, according to the relative size that is assigned to the medium size.
XS
S
M
XL
Smaller
Larger
L
Notes: Notes to the facilitator:
Explain the participants about T-shirt sizes for estimating the size of agile projects.
Notes to the participants:
T-Shirt sizes can be used for making high level estimates. T-shirt sizes can be used for estimating a large backlog of relative large items. This method will be useful especially when we have several concurrent scrum teams working on the same product. Items are estimated into T-shirt sizes: XS, S, M, L, XL, as given in the slide above. All the estimators will assign their own size to their items and a final consensus is reached to get a final estimate.
One of the disadvantages of this method is that the sizing may not be uniform. What seems to be L for someone, may be XL for someone else.

## Slide 10: What did You Grasp?
What is the ideal number of points can be completed in a single iteration?
  0-13
  15-18
  20-25
  25-30
State True or False. Affinity grouping is suitable only for projects with minimum number of items.
  True
  False
Notes: Notes to the Facilitator:
Tell the participants that they will be going through a knowledge check question.
Answers:
1. a. 0-13
2. b. False

## Slide 11: 1.35 Agile Implementation in Industry Projects
Implementation of Agile across organizations can be done by several approaches. Some of these for Developers and Management include:
Upper management
Customer Commitments
Tracking Progress
Impact on other groups
Project completion
Developers
Resistance
Micromanagement
Transition from traditional to Agile processes
Distributed development
Top talent is required
Enthusiastic teams
Testers
Notes: Notes to the Facilitator:
Explain the participants about the approaches in implementing Agile in industry projects.
Notes to the Participants:
So far, we have seen about Agile planning and estimation, which are critical steps in implementing any Agile project. This section lists down the various approaches through which Agile can be implemented in an organization.

## Slide 12: 1.36 Soft Skills in Agile
Soft skills refer to the interpersonal skills and the ability to interact effectively and harmoniously with other people.
Agile teams and the project leaders need to have soft skills, a few of them are as follows:
Soft Skills in Agile
Collaboration
Self-leadership
Adaptive leadership
Negotiation
Agile servant leadership
Agile coaching
Notes: Notes to the Facilitator:
List down and explain the most important soft skills that Agile project leaders should have.
Notes to the Participants:
Agile soft skills refer to the collaboration and leadership skills the Agile team members and leaders should possess. Some of the important ones are described below:
Collaboration: Collaboration refers to working together with others on a common goal that can otherwise not be achieved alone or by a single group. This may involve planning together, resource pooling and evaluating together. Customer collaboration is a good way to measure project success, by taking into account their feedback throughout the life cycle of a project.
Self-leadership: Agile leaders should lead themselves first in order to lead others. Agile leaders should avoid leaking emotions or projecting on others. They should practice what they preach and lead by example. They should have the clarity of what they want to do.
Adaptive leadership: The main aim of this is to adapt organizations to internal and external pressures for change. Adaptive leadership helps imbibe a positive work culture in an organization. Adaptive leadership is two-dimensional, i.e., being Agile and doing Agile. The four key levers for change that every Agile leader should start with, is:
Do Less
Speed-to-Value
Quality
Engage/Inspire
The four principles that adaptive leadership applies for encouraging the engagement of followers in helping the organization to adapt its environment are as follows:
Understanding the purpose of the organization
Utilization of people’s skills and expertise in helping with adaptation
Tolerating ambiguity
Freedom to act
Negotiation: Negotiation is a process by which two or more parties who are in conflict coming together to find a mutually acceptable resolution for the conflict. Successful negotiation needs to have the following qualities:
Separate people from the problem
Focus on interests, not positions
Invent options for mutual gain
Use objective criteria
Five level of conflicts
Agile servant leadership: Servant leadership refers to both a leadership philosophy and set of leadership practices. A servant leader has the qualities of deep listening, self-awareness and commitment to others. Agile leaders should not tell the teams what to do. They should help the team in the process of self-organization and expediting their progress. An example is that a Scrum master should ensure that the daily standup happens and is conducted in a proper way and estimate the team’s work.
Robert Greenleaf, the founder of the modern Servant Leadership has listed the principles of servant leadership which include listening, empathy, awareness, persuasion, conceptualization, foresight and stewardship.
Agile coaching: Agile coach helps the team grow strong in applying Agile practice to their work. Agile coaches should have the following qualities:
Coach the team through change
Accept the team’s ideas above their own
Navigate conflict
Integrate paths towards high performance

## Slide 13: What did You Grasp?
Which of the following could not be a soft skill of an Agile leader?
  Dictatorship
  Self-leadership
  Coaching
  Negotiation
Notes: Notes to the Facilitator:
Tell the participants that they will be going through a knowledge check question.
Answer:
1. a. Dictatorship

## Slide 14: 1.37 Lean Thinking
Lean methodology derives itself from Lean Principles in Manufacturing where more is achieved from less. Lean thinking is governed by core principles such as:
Lean Thinking
Minimization of waste
More learning
Late decision making
Quick delivery
Team empowerment
Build integrity
Holistic view
Notes: Notes to the Facilitator:
Explain to participants the principles behind lean thinking and how it can be applied to software development methodology.
Notes to the Participants:
Lean methodology was derived from lean principles that were applied in lean practices of manufacturing. The crux of the idea is to see how waste can be eliminated and how software development can be streamlined. In lean, waste is explain in a very broad sense and it refers to any activity that be eliminated to streamline the process.
Lean methodology in software is driven by the above mentioned principles of elimination of waste, amplified learning, an empowered team, fast delivery of features or functionality. Considering the high demand for products should be decided as late as possible in such a way that there is no rework. Most importantly, analyzing every single component of the process and having a holistic view is important in lean.

## Slide 15: 1.38 Lean Methodology: Customer is King
Lean places supreme importance on creating value for the customer.
Lean is delivering value to customers and continuously improving the ability to do this, by removing waste from the entire system that produces the value.
Lean
Notes: Notes to the Facilitator:
Explain to participant the principle of placing the customer before everything else.
Notes to the Participants:
Lean Methodology in software development forms the fundamental core on which many other methodologies such as Agile, MVP and DevOps came into existence. Lean methodology assesses the entire value system and development lifecycle for pitfalls/loopholes that causes waste in terms of time, man effort or quality. By studying the value and its components continuously, we focus of continuous improvement of the process and quick delivery of product.

## Slide 16: What did You Grasp?
Which of the following options is not a LEAN principle?
  Elimination of fees
  Slow delivery of features
  Late decision making
  Holistic approach
Notes: Notes to the Facilitator:
Answer:
1. B. Slow delivery of features

## Slide 17: In a nutshell, we learnt:
  Agile methodology
  Software, History of Software Engineering and Software Development Methodologies
  Traditional Software Development Models
  Waterfall Model, Classical Waterfall Model
  Traditional IT Organizations
  Developers vs IT Operations Conflict
  Birth of Agile, Four Values of the Agile Manifesto
  Scrum, Scrum Theory, Scrum Values, Scrum Roles, Scrum Master Scrum Sprints, Benefits of Scrum
  Planning and Estimation, Agile Planning, Levels of Agile Planning

## Slide 18: In a nutshell, we learnt (Contd.):
  Conditions of Satisfaction, Velocity
  Estimating Techniques
  Soft Skills in Agile

## Slide 19
Next Module 2: Introduction to Software Craftsmanship