## Slide 1: KANBAN WORKFLOW
Christel Ginevro – cgi@voxteneo.com +32 (0)2 743 37 78

## Slide 2: Kanban Workflow
Assignable
Business Value & Severity
Evaluate the effort
The status
Some more rules
Vox Teneo | Kanban Workflow

## Slide 3: 1
Vox Teneo | Kanban Workflow
THE
ASSIGNABLE
– User stories, Bugs, Features…

## Slide 4: What is an Assignable?
Assignable = ticket
There are 4 of them on TargetProcess (TP):
Feature
User Story
Task
Bug
Vox Teneo | Kanban Workflow

## Slide 5: What is a User Story?
A User story has Business value
User story: add a slider on the homepage Business value: promote his products
Not a user story: add a slider plugin in the administration No business value, it only allows you to create the slider
A User story is “small”: you can evaluate it by itself
“Create a slider” has an effort 2 (see later)
“Create the whole homepage”… it depends what you
want on the homepage
Vox Teneo | Kanban Workflow

## Slide 6: What is a Task?
= technical acts
= part of a User story
A User story contains several tasks
Example:
User story = create a slider
Task 1: install the plugin
Task 2: create the custom post type
Task 3: cut & slice
Task 4: deploy to staging
Vox Teneo | Kanban Workflow
User story
T1
T4
T2
T3

## Slide 7: What is a Feature?
= big User story
= includes several User stories
A User story can be part of a Feature
Example:
Feature = create homepage
US1: create slider
US2: show last news
US3: show one random testimonial
Vox Teneo | Kanban Workflow
Feature
U1
U4
U2
U3

## Slide 8: Summary for US, Features & Tasks Feature
1 feature = several US 1 US = several tasks
1 task is usually part of 1 US
1 US isn’t always part
of 1 feature
Vox Teneo | Kanban Workflow
User story
T1
T4
T2
T3
User story
T1
T4
T2
T3
User story
T1
T4
T2
T3

## Slide 9: What is a Bug?
= an item already developed but not acting normally No business value
Not billed to the client
Bug: nothing happens when I click on the button The button is there and should already work
Not a bug: I would like to add a button as a shortcut to the contact page
It has a value: it’s a call-to-action to help users
Vox Teneo | Kanban Workflow

## Slide 10: 2VALUE
Vox Teneo | Kanban Workflow
BUSINESS
– And Severity

## Slide 11: Business Value (US)
Defines User Stories
First step toward priority
What is the second step?
Evaluation
Example:
-US1: BV “Good”, 13 points
-US2: BV “Average”, 1 point Perhaps interesting to do US2 first
Vox Teneo | Kanban Workflow

## Slide 12: Business Value (US)
Must Have
Great
Good
Average
Nice to have
Notes:
Defining BV & Priority is the PM job
But it’s good for you to know how important the US you are working on is
Vox Teneo | Kanban Workflow

## Slide 13: Business Value & Severity (bugs)
Bug = item already developed but not acting normally It makes us look unprofessional
It should be solved
Business Value for bugs:
Fix ASAP
Fix if Time
Depends on the importance of the Project
Vox Teneo | Kanban Workflow

## Slide 14: Business Value & Severity (bugs)
Severity:
Blocking: nothing is working on prod! You stop to work on your US to solve the bug
Critical: something big stopped working on prod: better to also stop working on your US to solve the bug
Normal: you work on it as soon as you’re done with your current US
Small: PM will give priority along with US
Enhancement: PM will give priority along with US
Vox Teneo | Kanban Workflow

## Slide 15: 3THE EFFORT
Vox Teneo | Kanban Workflow
EVALUATE

## Slide 16: How to evaluate the effort?
Not in hours => in points
Only for User Stories. The features effort is all its US efforts put together.
What does the evaluation depends on?
Relative effort
Time
Example:
-Login system on WP: easy but lots of Tasks
-SSO from e-shop to ERP: complex
Vox Teneo | Kanban Workflow

## Slide 17
How to evaluate effort?
Vox Teneo | Kanban Workflow
Example of the tennis ball

## Slide 18
How to evaluate effort?
Vox Teneo | Kanban Workflow
Example of the tennis ball

## Slide 19
How to evaluate effort?
Vox Teneo | Kanban Workflow
Example of the tennis ball

## Slide 20
How to evaluate effort?
Vox Teneo | Kanban Workflow
Example of the tennis ball
Relative effort

## Slide 21: What are the level of effort?
1, 2, 3, 5, 8, 13, 20, 40, 100, YMBK (= You Must Be Kidding)
If it feels like 4 => 5
If it feels like 9 => 13
YMBK case for a User Story
It should be a feature
Ask the PM to change it to feature and to create several User Stories for it
Vox Teneo | Kanban Workflow

## Slide 22
What if information is missing?
The ticket is not Planned It should be in Backlog
Vox Teneo | Kanban Workflow

## Slide 23: Why should the team estimate?
PM has no idea of how the US will be implemented
Everybody in the team doesn’t know how to do it either (juniors or just you never had to do that before)
People can’t cheat (it’s very hard!) if everyone is looking
Seniors can’t tell to juniors “it’s easy!” if the junior thinks it’s complicated
Task estimated > 5 points : not for juniors
Vox Teneo | Kanban Workflow

## Slide 24: 4STATUS
Vox Teneo | Kanban Workflow
THE
– Backlog, Ready, In Testing, Done

## Slide 25: For Features, Tasks & Bugs
The flow is limited Features depend on US
Tasks can’t be deployed and tested, only US can
Bugs should be fixed directly where the problem is
Vox Teneo | Kanban Workflow

## Slide 26: For User Stories
Backlog
Planned
Ready
In Progress
In Review
In Testing
Ready for QA
In QA
Done
Note: details on http://intranet.voxteneo.com/wiki/Scrum_and_Kanban_at_Vox_Teneo
Vox Teneo | Kanban Workflow

## Slide 27: Backlog
“The PM created the ticket to define the story/bug but the ticket is not complete yet”
It’s a draft
Normally, when a project begins, all US should be in the Backlog so you can see the full project since the beginning.
To get out of Backlog, a ticket should have:
A description with all needed details to evaluate
A Business Value (if US) or a Severity (if Bug)
Test cases
Vox Teneo | Kanban Workflow

## Slide 28: Planned
If a ticket is “Planned”, it should have:
A description with all needed details to evaluate
A Business Value (US) or a Severity (Bug)
Test cases
It must be understood in the same way by Dev and PM!
If something is missing, it can’t be Planned!
Move on to next ticket or contact the PM to ask him for information
If nothing is missing, the team should evaluate the effort
Vox Teneo | Kanban Workflow

## Slide 29: Ready
= You can start working on the ticket
= the PMs defined the priorities: ticket on top first
In Vox Teneo: usually, 1-week plan, the tickets stays in “Planned” even if evaluated for following weeks
/!\ If the PM puts the ticket directly to Ready Check if the ticket is OK for Planned Evaluate the task
If you have too much for one week: talk with the PM
Vox Teneo | Kanban Workflow

## Slide 30: In Progress
= You are working on the ticket
Two important points:
ONLY ONE at the time (or you have two computers)
ALWAYS ONE (or you’re not doing anything)
This means:
You should finish a US before starting another Exception: bugs
You should always be doing something
Exception: holidays
Vox Teneo | Kanban Workflow

## Slide 31: In Review
= Another Developer is Reviewing your code / your work
This status was added at the devs’ request
If a ticket is “In Review”, don’t forget to assign it to a Reviewer
Vox Teneo | Kanban Workflow

## Slide 32: In Testing
= the ticket is ready to be tested
All Tasks are “Done”
The scope of the US is reached
The PM has access to a test platform (staging, etc.)
You have timesheeted
If the PM can’t test it, it’s not In Testing, it’s still In Progress You can’t start another US (only one In Progress)
Only possible if the US is the right size (no need to test each task one by one, not too big to be a US)
Note: if it’s not In Testing, the PM won’t test it!
Vox Teneo | Kanban Workflow

## Slide 33: Ready for QA
= the ticket has been tested and validated. It can now be tested by the customer
If there’s a bug later, the dev and the tester should have seen it
The ticket should be deployed in QA
Vox Teneo | Kanban Workflow

## Slide 34: In QA / Done
In QA = the ticket can be tested by the customer
Done = the ticket has been validated by PM and/or
customer
If bugs or additional request appears New ticket
The ticket shouldn’t go back in the flow!
Vox Teneo | Kanban Workflow

## Slide 35: 5RULES
Vox Teneo | Kanban Workflow
SOME MORE

## Slide 36: I don’t have a ticket!
Then you don’t do the work. Seriously.
Ask the PM for a ticket!
Why?
You don’t have the information or could forget
The other PMs don’t know what you’re working on
Vox Teneo | Kanban Workflow

## Slide 37: I don’t have a ticket!
Special case, the ticket is on Redmine:
If the PM is busy, you can move the ticket to TP yourself Put the link to new TP ticket on the old Redmine ticket
Special case 2, I help another dev:
Assign the ticket to the both of you, in TP, it’s possible!
Vox Teneo | Kanban Workflow

## Slide 38: Interruptions
US estimated <= 5 points: no interruption possible, excepted by blocking bug
US estimated > 5 points: interruption only after the
current intermediate task is completed
Vox Teneo | Kanban Workflow

## Slide 39: Impediments
Examples:
Priorities keep changing
There’s noise in the office because of the construction
My PC isn’t working
I don’t have access to server
I don’t understand the US
Do something about it Ask the PM
The PM task is also to make your life easier
And he should know if he can help
Vox Teneo | Kanban Workflow

## Slide 40: THANK YOU FOR LISTENING
Vox Teneo | Kanban Workflow